## Influence - Interest Matrix
| Interest (1-10) | Influence (1-10) | Advocate? (Y/N) | LABEL | ADVOCATE | DETRACTOR | NEUTRAL
Person 1 | 2 | 3 | DETRACTOR | P1 | #N/A | 3 | #N/A
Person 2 | 3 | 2 | ADVOCATE | P2 | 2 | #N/A | #N/A
Person 3 | 2 | 4 | NEUTRAL | P3 | #N/A | #N/A | 4
Person 4 | 3 | 4 | ADVOCATE | P4 | 4 | #N/A | #N/A
Person 5 | 1 | 1 | ADVOCATE | P5 | 1 | #N/A | #N/A
Person 6 | 9 | 9 | DETRACTOR | P6 | #N/A | 9 | #N/A
Person 7 | 6 | 4 | DETRACTOR | P7 | #N/A | 4 | #N/A
Person 8 | 7 | 3 | ADVOCATE | P8 | 3 | #N/A | #N/A
Person 9 | 8 | 6 | DETRACTOR | P9 | #N/A | 6 | #N/A
Person A | 2 | 7 | DETRACTOR | PA | #N/A | 7 | #N/A
Person B | 8 | 2 | ADVOCATE | PB | 2 | #N/A | #N/A
Person C | 2 | 1 | DETRACTOR | PC | #N/A | 1 | #N/A
Person D | 5 | 7 | ADVOCATE | PD | 7 | #N/A | #N/A
MANAGE CLOSELY
KEEP SATISFIED
MONITOR
KEEP INFORMED

## Stakeholder Management Plan
Stakeholder | I/I Quadrant | Sentiment | What they expect from me | What I need from them | Development needed? If so, explain goal | Approach | Type / Frequency of communication
Person 1 | Monitor | DETRACTOR | To deliver the project within budget and keep them up-to-date | To influence the other committee members to support the project | Move to Advocate | Emphasise competitive benefits | Quarterly board meeting Weekly catch-up
Person 2 | Monitor | ADVOCATE | To support their team in delivering the change | Remove blockers in their team if required | No - maintain |  | Monthly catch-up
Person 3 | Monitor | NEUTRAL
Person 4 | Monitor | ADVOCATE
Person 5 | Monitor | ADVOCATE
Person 6 | Manage Closely | DETRACTOR
Person 7 | Keep Informed | DETRACTOR
Person 8 | Keep Informed | ADVOCATE
Person 9 | Manage Closely | DETRACTOR
Person A | Keep Satisfied | DETRACTOR
Person B | Keep Informed | ADVOCATE
Person C | Monitor | DETRACTOR
Person D | Keep Satisfied | ADVOCATE

## Lookups
Quadrant Lookup | Influence
interest | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Monitor | Monitor | Monitor | Monitor | Monitor | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied
2 | Monitor | Monitor | Monitor | Monitor | Monitor | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied
3 | Monitor | Monitor | Monitor | Monitor | Monitor | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied
4 | Monitor | Monitor | Monitor | Monitor | Monitor | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied
5 | Monitor | Monitor | Monitor | Monitor | Monitor | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied | Keep Satisfied
6 | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Manage Closely | Manage Closely | Manage Closely | Manage Closely | Manage Closely
7 | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Manage Closely | Manage Closely | Manage Closely | Manage Closely | Manage Closely
8 | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Manage Closely | Manage Closely | Manage Closely | Manage Closely | Manage Closely
9 | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Manage Closely | Manage Closely | Manage Closely | Manage Closely | Manage Closely
10 | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Keep Informed | Manage Closely | Manage Closely | Manage Closely | Manage Closely | Manage Closely